## Overal
PROJECT MASTER PLAN
Project Name |  |  | Residential Communication Channel |  | Overall Weeks
Project Manager Name |  |  | Vinh Nguyen |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30
Iterarion | Status | Tasks |  | Assigned to
1 | Open | Prepare document, training for project Architecture Design Functional Requirement in High Level |  | GENTLEMAN TEAM | Overall Weeks Week 1: Wed 10/10/18; Overall Weeks Week 2: X; Overall Weeks Week 3: Wed 24/10/18
2 | Open | Development Feature Chat |  | GENTLEMAN TEAM | bar: Overall Weeks Week 10 to Overall Weeks Week 16
3 | Open | Development Feature Notification & User Dashboard |  | GENTLEMAN TEAM | bar: Overall Weeks Week 17 to Overall Weeks Week 23
4 | Open | Development Feature left |  | GENTLEMAN TEAM | bar: Overall Weeks Week 24 to Overall Weeks Week 30

## Iter1_DetailPlan
PROJECT DETAIL PLAN FOR ITERATION 1
Project Name |  |  | Residential Communication Channel |  |  |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9
Project Manager Name |  |  | Vinh Nguyen | time axis 2018-10-07 to 2018-12-08
Task ID | Status | Tasks |  | Assigned to | Validate by | Estimate (Hour) | Total Actual (Hour)
1 | Close | Team Kick off Meeting |  | GENTLEMAN TEAM | Vinh Nguyen | 2 | 2 | 2018-10-07: 2
2 | Close | Prepare for Team Training Plan |  | Vinh Nguyen | Vinh Nguyen | 1 | 1 | bar: 2018-10-08
3 | Close | Prepare Team Charter |  | Vinh Nguyen | Vinh Nguyen | 1 | 1 | bar: 2018-10-08
4 | Close | Prepare Repository for document |  | Vinh Nguyen | Vinh Nguyen | 1 | 1 | bar: 2018-10-09
5 | Close | Prepare Team Training |  | GENTLEMAN TEAM | Vinh Nguyen | 1 | 1 | bar: 2018-10-10
6 | Close | Team Training Phase 1 |  | GENTLEMAN TEAM | Vinh Nguyen | 54 | 40 | 2018-10-11: 14; 2018-10-12: 11; 2018-10-13: 15
7 | Close | Team Training Phase 2 |  | GENTLEMAN TEAM | Vinh Nguyen | 126 | 61.5 | 2018-10-14: 3.5; 2018-10-15: 9; 2018-10-16: 10.5; 2018-10-17: 12; 2018-10-18: 7.5; 2018-10-19: 4; 2018-10-20: 15
8 | Close | Team Training Phase 3 |  | GENTLEMAN TEAM | Vinh Nguyen | 54 | 21 | 2018-10-21: 4.5; 2018-10-22: 9; 2018-10-23: 7.5
9 | In Progress | Prepare Master Plan & Detail Plan |  | Vinh Nguyen | Vinh Nguyen | 5 | 4 | 2018-10-26: 2; 2018-10-27: 2
10 | In Progress | Prepare and Update Configuration Management |  | Hau Vo | Vinh Nguyen | 5 | 5 | 2018-10-24: 1; 2018-10-25: 2; 2018-10-26: 2
11 | In Progress | Prepare and Update Communication Management |  | An Pham | Vinh Nguyen | 5 | 3 | bar: 2018-10-24; 2018-10-26 to 2018-10-27
12 | In Progress | Prepare and Update Change Management |  | Quan Ngo | Vinh Nguyen | 5 | 5 | 2018-10-24: 1; 2018-10-25: 2; 2018-10-27: 2
13 | In Progress | Prepare and Update Risk Management |  | Lam To | Vinh Nguyen | 5 | 5 | 2018-10-24: 1; 2018-10-25: 2; 2018-10-27: 2
14 | In Progress | Prepare and Update Project Plan |  | Manh Truong | Vinh Nguyen | 5 | 5 | 2018-10-24: 1; 2018-10-27: 3; 2018-10-28: 1
15 | Open | Prepare and Update Quality Management |  | GENTLEMAN TEAM | Vinh Nguyen | 10 | 0
16 | Open | Analyze Architecture Driver |  | GENTLEMAN TEAM | Vinh Nguyen
17 | Open | Gather High Level Requirement |  | GENTLEMAN TEAM | Vinh Nguyen
18 | Open
19 | Open
20 | Open
21 | Open
22 | Open
23 | Open
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174

## Iter2_DetailPlan
PROJECT DETAIL PLAN FOR ITERATION 2
Project Name |  |  | Residential Communication Channel |  |  |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7
Project Manager Name |  |  | Vinh Nguyen | time axis 2018-12-09 to 2019-01-26
Task ID | Status | Tasks |  | Assigned to | Validate by | Estimate (Hour) | Total Actual (Hour)
1 | [6 empty] | 0
2 | [6 empty] | 0
3 | [6 empty] | 0
4 | [6 empty] | 0
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174

## Iter3_DetailPlan
PROJECT DETAIL PLAN FOR ITERATION 3
Project Name |  |  | Residential Communication Channel |  |  |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7
Project Manager Name |  |  | Vinh Nguyen | time axis 2019-02-17 to 2019-04-06
Task ID | Status | Tasks |  | Assigned to | Validate by | Estimate (Hour) | Total Actual (Hour)
1 | Close | Team Kick off Meeting |  | GENTLEMAN TEAM | Vinh Nguyen | 2 | 2 | 2019-02-17: 2
2 | Close | Prepare for Team Training Plan |  | Vinh Nguyen | Vinh Nguyen | 1 | 1 | bar: 2019-02-18
3 | Close | Prepare Team Charter |  | Vinh Nguyen | Vinh Nguyen | 1 | 1 | bar: 2019-02-18
4 | Open | Prepare Repository for document |  | Vinh Nguyen | Vinh Nguyen | 1 | 1 | bar: 2019-02-19
5 |  | Prepare |  | GENTLEMAN TEAM |  |  | 0
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174

## Iter4_DetailPlan
PROJECT DETAIL PLAN FOR ITERATION 4
Project Name |  |  | Residential Communication Channel |  |  |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7
Project Manager Name |  |  | Vinh Nguyen | time axis 2019-04-07 to 2019-05-25
Task ID | Status | Tasks |  | Assigned to | Validate by | Estimate (Hour) | Total Actual (Hour)
1 | Close | Team Kick off Meeting |  | GENTLEMAN TEAM | Vinh Nguyen | 2 | 2 | 2019-04-07: 2
2 | Close | Prepare for Team Training Plan |  | Vinh Nguyen | Vinh Nguyen | 1 | 1 | bar: 2019-04-08
3 | Close | Prepare Team Charter |  | Vinh Nguyen | Vinh Nguyen | 1 | 1 | bar: 2019-04-08
4 | Open | Prepare Repository for document |  | Vinh Nguyen | Vinh Nguyen | 1 | 1 | bar: 2019-04-09
5 |  | Prepare |  | GENTLEMAN TEAM |  |  | 0
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174

## Tools
Open | Vinh Nguyen
In Progress | Manh Truong
Close | Lam To
Hau Vo
Quan Ngo
An Pham
GENTLEMAN TEAM