## Total
Residential Communication Channel
Earned Value Analysis Report
| Prepared By: | Vinh Nguyen
| Date: | 2018-06-11
[42]
| For Period: | Iteration 1
Note:
Tuần 1 - 3 : Sẽ có 6 ngày làm viêc ( trừ CN) và quy định mỗi thành viên làm việc 3h/ ngày, tổng số thành viên sẽ làm việc 18h/ ngày và 1 tuần sẽ là 108h/ tuần. Tuần 4 - 9 : Sẽ có 6 ngày làm việc ( trừ CN) và quy định mỗi thành viên làm việc 4h/ ngày, tổng số thành viên làm việc 24h/ ngày và 1 tuần sẽ là 144h/ tuần.
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | Total Hour | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9
1.1 | Team Kick off Meeting | 2 | W1: 2
1.2 | Prepare for Team Training Plan | 1 | bar: W1
1.3 | Prepare Team Charter | 1 | bar: W1
1.4 | Prepare Repository for document | 1 | bar: W1
1.5 | Prepare Team Training | 1 | bar: W1
1.6 | Team Training Phase 1 - Mobile and Web | 54 | W1: 54
1.7 | Team Training Phase 2 - Mobile, Data and Web | 108 | W2: 108
1.8 | Team Training Phase 3 - Review all research | 36 | W3: 36
1.9 | Prepare Master Plan & Detail Plan | 5 | W3: 5
1.10 | Prepare and Update Configuration Management | 5 | W3: 5
1.11 | Prepare and Update Communication Management | 5 | W3: 5
1.12 | Prepare and Update Change Management | 5 | W3: 5
1.13 | Prepare and Update Risk Management | 5 | W3: 5
1.14 | Prepare and Update Project Plan | 5 | W3: 5
1.15 | Identify Process & Quality Management | 2 | W3: 2
1.16 | Gather High Level Requirement | 3 | W3: 3
1.17 | Draw Business Process and Verifiy with Customer | 6 | W3: 2; W4: 4
1.18 | Update Document for Project | 5 | W4: 5
1.19 | Team Training Phase 4 - Research & Demo Login Function | 144 | W4: 72; W5: 72
1.20 | Update Business Process | 6 | W4: 2; W5: 4
1.21 | Identify Architecture Phase 1 - Identify Constraint and Quality | 6 | W4: 2; W5: 4
1.22 | Do Process and Quality Management | 5 | W4: 1; W5: 4
1.23 | Identify Architecture Phase 2 - Continues to identify Quality | 10 | W5: 5; W6: 5
1.24 | Prepare Architecture Design Template | 5 | W5: 3; W6: 2
1.25 | Write and Prove Scenario for Security Attribute for Customer | 5 | W5: 4; W6: 1
1.26 | Research about N - Tier Architecture | 32 | W5: 8; W6: 24
1.27 | Research about RealTime Pattern | 32 | W5: 8; W6: 24
1.28 | Research about Unit of Works Layer | 18 | W5: 4; W6: 14
1.29 | Research about Repository Layer | 18 | W5: 4; W6: 14
1.30 | Research about Business Layer | 18 | W5: 4; W6: 14
1.31 | Update Architect Driver Document | 4 | W5: 1; W6: 3
1.32 | Research ReactNative | 24 | W5: 6; W6: 18
1.33 | Support Research ReactNative | 24 | W5: 6; W6: 18
1.34 | Identify about more Quality of System and Pattern | 108 | W7: 108
1.35 | Identify and Write Scenario for Quality Compatibility, Performance, Maintainability,Authenticity | 12 | W7: 12
1.36 | Research about Micro Service Pattern | 6 | W7: 4; W8: 2
1.37 | Identify Architecture Phase 3 - Make Design View to solve the Constraint, Quality and High Level Requirement | 20 | W8: 20
1.38 | Gather Requirement for Core System | 3 | W8: 3
1.39 | Confirm Identified Qualities for System | 2 | W8: 2
1.40 | Draw Business Process for API Core System ( User, Role, Domain ) | 20 | W8: 20
1.41 | Review Static View of System | 2 | W8: 2
1.42 | Draw Business Process for API Core System ( Login, Register) | 72
1.43 | Implement Microservice for Login, Register using Token | 72
1.44 | Confirm Architecture View for System | 3
1.45
1.46
1.47
Insert new rows above this one
| Total Hour | 921 | 60 | 108 | 73 | 86 | 137 | 137 | 124 | 49 | 0
|  | Cumulative Planned Value (PV) | 60 | 168 | 241 | 327 | 464 | 601 | 725 | 774 | 774
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 46 | 107.5 | 161.5 | 238.5 | 359.5 | 490.5 | 612.5 | 659.5 | 659.5
|  | Cumulative Earned Value (EV) | 46 | 61.5 | 56 | 153.5 | 315 | 182.0952 | 124 | 51 | 0
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | 0 | -46 | -105.5 | -85 | -44.5 | -308.4048 | -488.5 | -608.5 | -659.5
|  | Schedule Variance (SV = EV - PV) | -14 | -106.5 | -185 | -173.5 | -149 | -418.9048 | -601 | -723 | -774
|  | Cost Performance Index (CPI = EV/AC) | 1 | 0.57209 | 0.34675 | 0.64361 | 0.87622 | 0.37124 | 0.20245 | 0.077331 | 0
|  | Schedule Performance Index (SPI = EV/PV) | 0.76667 | 0.36607 | 0.23237 | 0.46942 | 0.67888 | 0.30299 | 0.17103 | 0.065891 | 0
|  | Estimated Cost at Completion (EAC) | 921 | 1609.878 | 2656.0982 | 1431 | 1051.1095 | 2480.8474 | 4549.2944 | 11909.7941 | #DIV/0!
Note on A21: Work Breakdown Structure (WBS)

## AC
Actual Cost for Iteration 1
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period.
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Transfer the Cumulative Actual Cost to the Report worksheet.
Actual Cost (AC) of Work Performed
WBS | Task Name | Total | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9
1.1 | Team Kick off Meeting | 2 | 2
1.2 | Prepare for Team Training Plan | 1 | 1
1.3 | Prepare Team Charter | 1 | 1
1.4 | Prepare Repository for document | 1 | 1
1.5 | Prepare Team Training | 1 | 1
1.6 | Team Training Phase 1 - Mobile and Web | 40 | 40
1.7 | Team Training Phase 2 - Mobile, Data and Web | 61.5 |  | 61.5
1.8 | Team Training Phase 3 - Review all research | 23 |  |  | 23
1.9 | Prepare Master Plan & Detail Plan | 4 |  |  | 4
1.10 | Prepare and Update Configuration Management | 5 |  |  | 5
1.11 | Prepare and Update Communication Management | 3 |  |  | 3
1.12 | Prepare and Update Change Management | 5 |  |  | 5
1.13 | Prepare and Update Risk Management | 5 |  |  | 5
1.14 | Prepare and Update Project Plan | 5 |  |  | 5
1.15 | Identify Process & Quality Management | 1 |  |  | 1
1.16 | Gather High Level Requirement | 2 |  |  | 2
1.17 | Draw Business Process and Verifiy with Customer | 4 |  |  | 1 | 3
1.18 | Update Document for Project | 5 |  |  |  | 5
1.19 | Team Training Phase 4 - Research & Demo Login Function | 128 |  |  |  | 65 | 63
1.20 | Update Business Process | 5 |  |  |  | 2 | 3
1.21 | Identify Architecture Phase 1 - Identify Constraint and Quality | 4 |  |  |  | 1 | 3
1.22 | Do Process and Quality Management | 4 |  |  |  | 1 | 3
1.23 | Identify Architecture Phase 2 - Continues to identify Quality | 10 |  |  |  |  | 5 | 5
1.24 | Prepare Architecture Design Template | 5 |  |  |  |  | 3 | 2
1.25 | Write and Prove Scenario for Security Attribute for Customer | 4 |  |  |  |  | 3 | 1
1.26 | Research about N - Tier Architecture | 31 |  |  |  |  | 8 | 23
1.27 | Research about RealTime Pattern | 28 |  |  |  |  | 6 | 22
1.28 | Research about Unit of Works Layer | 17 |  |  |  |  | 3 | 14
1.29 | Research about Repository Layer | 17 |  |  |  |  | 4 | 13
1.30 | Research about Business Layer | 17 |  |  |  |  | 4 | 13
1.31 | Update Architect Driver Document | 4 |  |  |  |  | 1 | 3
1.32 | Research ReactNative | 24 |  |  |  |  | 6 | 18
1.33 | Support Research ReactNative | 23 |  |  |  |  | 6 | 17
1.34 | Identify about more Quality of System and Pattern | 107 | [6 empty] | 107
1.35 | Identify and Write Scenario for Quality Compatibility, Performance, Maintainability,Authenticity | 11 | [6 empty] | 11
1.36 | Research about Micro Service Pattern | 6 | [6 empty] | 4 | 2
1.37 | Identify Architecture Phase 3 - Make Design View to solve the Constraint, Quality and High Level Requirement | 20 | [7 empty] | 20
1.38 | Gather Requirement for Core System | 3 | [7 empty] | 3
1.39 | Confirm Identified Qualities for System | 2 | [7 empty] | 2
1.40 | Draw Business Process for API Core System ( User, Role, Domain ) | 18 | [7 empty] | 18
1.41 | Review Static View of System | 2 | [7 empty] | 2
1.42 | Draw Business Process for API Core System ( Login, Register) | 0
1.43 | Implement Microservice for Login, Register using Token | 0
Insert new rows above this one
|  | Total Actual Cost | 46 | 61.5 | 54 | 77 | 121 | 131 | 122 | 47 | 0
|  | Cumulative Actual Cost (AC) | 46 | 107.5 | 161.5 | 238.5 | 359.5 | 490.5 | 612.5 | 659.5 | 659.5

## EV
Earned Value for Iteration 1
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP).
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV)
WBS | Task Name | Total Hour | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9
1.1 | Team Kick off Meeting | 2 | Wk 1: 100%
1.2 | Prepare for Team Training Plan | 1 | Wk 1: 100%
1.3 | Prepare Team Charter | 1 | Wk 1: 100%
1.4 | Prepare Repository for document | 1 | Wk 1: 100%
1.5 | Prepare Team Training | 1 | Wk 1: 100%
1.6 | Team Training Phase 1 - Mobile and Web | 54 | Wk 1: 74.07%
1.7 | Team Training Phase 2 - Mobile, Data and Web | 108 | Wk 2: 56.94%
1.8 | Team Training Phase 3 - Review all research | 36 | Wk 3: 63.89%
1.9 | Prepare Master Plan & Detail Plan | 5 | Wk 3: 80%
1.10 | Prepare and Update Configuration Management | 5 | Wk 3: 100%
1.11 | Prepare and Update Communication Management | 5 | Wk 3: 60%
1.12 | Prepare and Update Change Management | 5 | Wk 3: 100%
1.13 | Prepare and Update Risk Management | 5 | Wk 3: 100%
1.14 | Prepare and Update Project Plan | 5 | Wk 3: 100%
1.15 | Identify Process & Quality Management | 2 | Wk 3: 50%
1.16 | Gather High Level Requirement | 3 | Wk 3: 66.67%
1.17 | Draw Business Process and Verifiy with Customer | 6 | Wk 3: 50%; Wk 4: 75%
1.18 | Update Document for Project | 5 | Wk 4: 100%
1.19 | Team Training Phase 4 - Research & Demo Login Function | 144 | Wk 4: 90.28%; Wk 5: 87.5%
1.20 | Update Business Process | 6 | Wk 4: 100%; Wk 5: 75%
1.21 | Identify Architecture Phase 1 - Identify Constraint and Quality | 6 | Wk 4: 50%; Wk 5: 75%
1.22 | Do Process and Quality Management | 5 | Wk 4: 100%; Wk 5: 75%
1.23 | Identify Architecture Phase 2 - Continues to identify Quality | 10 | Wk 5: 100%; Wk 6: 100%
1.24 | Prepare Architecture Design Template | 5 | Wk 5: 100%; Wk 6: 100%
1.25 | Write and Prove Scenario for Security Attribute for Customer | 5 | Wk 5: 75%; Wk 6: 100%
1.26 | Research about N - Tier Architecture | 32 | Wk 5: 100%; Wk 6: 95.83%
1.27 | Research about RealTime Pattern | 32 | Wk 5: 75%; Wk 6: 91.67%
1.28 | Research about Unit of Works Layer | 18 | Wk 5: 75%; Wk 6: 100%
1.29 | Research about Repository Layer | 18 | Wk 5: 100%; Wk 6: 92.86%
1.30 | Research about Business Layer | 18 | Wk 5: 100%; Wk 6: 92.86%
1.31 | Update Architect Driver Document | 4 | Wk 5: 100%; Wk 6: 100%
1.32 | Research ReactNative | 24 | Wk 5: 100%; Wk 6: 100%
1.33 | Support Research ReactNative | 24 | Wk 5: 100%; Wk 6: 94.44%
1.34 | Identify about more Quality of System and Pattern | 108 | Wk 7: 99.07%
1.35 | Identify and Write Scenario for Quality Compatibility, Performance, Maintainability,Authenticity | 12 | Wk 7: 91.67%
1.36 | Research about Micro Service Pattern | 6 | Wk 7: 100%; Wk 8: 100%
1.37 | Identify Architecture Phase 3 - Make Design View to solve the Constraint, Quality and High Level Requirement | 20 | Wk 8: 100%
1.38 | Gather Requirement for Core System | 3 | Wk 8: 100%
1.39 | Confirm Identified Qualities for System | 2 | Wk 8: 100%
1.40 | Draw Business Process for API Core System ( User, Role, Domain ) | 20 | Wk 8: 90%
1.41 | Review Static View of System | 2 | Wk 8: 100%
Insert new rows above this one
|  | Cumulative EV | 46 | 61.5 | 56 | 153.5 | 315 | 182.0952 | 124 | 51 | 0
Open
On-Going
Close
Re-Open

## W1
Earned Value for Week 1
Cumulative Earned Value (EV)
WBS | Task Name | Total Hour | 2018-10-08 | 2018-10-09 | 2018-10-10 | 2018-10-11 | 2018-10-12 | 2018-10-13 | Total
1.1 | Team Kick off Meeting | 2 | 100% | 0% | 0% | 0% | 0% | 0% | 100%
1.2 | Prepare for Team Training Plan | 1 | 0% | 100% | 0% | 0% | 0% | 0% | 100%
1.3 | Prepare Team Charter | 1 | 0% | 100% | 0% | 0% | 0% | 0% | 100%
1.4 | Prepare Repository for document | 1 | 0% | 0% | 100% | 0% | 0% | 0% | 100%
1.5 | Prepare Team Training | 1 | 0% | 0% | 100% | 0% | 0% | 0% | 100%
| Team Training Phase 1 - Mobile and Web | 54 | 0% | 0% | 0% | 25.93% | 20.37% | 27.78% | 74.07%
Insert new rows above this one
|  | Cumulative EV | 2 | 2 | 2 | 14 | 11 | 15
Actual Cost for Week 1
Actual Cost (AC) of Work Performed
WBS | Task Name |  | 2018-10-08 | 2018-10-09 | 2018-10-10 | 2018-10-11 | 2018-10-12 | 2018-10-13 | Status
1.1 | Team Kick off Meeting | 2 | 2 | [5 empty] | Close
1.2 | Prepare for Team Training Plan | 1 |  | 1 |  |  |  |  | Close
1.3 | Prepare Team Charter | 1 |  | 1 |  |  |  |  | Close
1.4 | Prepare Repository for document | 1 |  |  | 1 |  |  |  | Close
1.5 | Prepare Team Training | 1 |  |  | 1 |  |  |  | Close
1.6 | Team Training Phase 1 - Mobile and Web | 40 |  |  |  | 14 | 11 | 15 | Close
Insert new rows above this one
|  | Total Actual Cost | 2 | 2 | 2 | 14 | 11 | 15
|  | Cumulative Actual Cost (AC) | 2 | 4 | 6 | 20 | 31 | 46

## W2
Earned Value for Week 2
Cumulative Earned Value (EV)
WBS | Task Name | Total Hour | 2018-10-15 | 2018-10-16 | 2018-10-17 | 2018-10-18 | 2018-10-19 | 2018-10-20 | Total
1.7 | Team Training Phase 2 - Mobile, Data and Web | 108 | 11.57% | 9.722% | 11.11% | 6.944% | 3.704% | 13.89% | 56.94%
Insert new rows above this one
|  | Cumulative EV | 12.5 | 10.5 | 12 | 7.5 | 4 | 15
Actual Cost for Week 2
Actual Cost (AC) of Work Performed
WBS | Task Name |  | 2018-10-15 | 2018-10-16 | 2018-10-17 | 2018-10-18 | 2018-10-19 | 2018-10-20 | Status
1.7 | Team Training Phase 2 - Mobile, Data and Web | 61.5 | 12.5 | 10.5 | 12 | 7.5 | 4 | 15 | Close
Insert new rows above this one
|  | Total Actual Cost | 12.5 | 10.5 | 12 | 7.5 | 4 | 15
|  | Cumulative Actual Cost (AC) | 12.5 | 23 | 35 | 42.5 | 46.5 | 61.5

## W3
Earned Value for Week 3
Cumulative Earned Value (EV)
WBS | Task Name | Total Hour | 2018-10-22 | 2018-10-23 | 2018-10-24 | 2018-10-25 | 2018-10-26 | 2018-10-27 | Total
1.8 | Team Training Phase 3 - Review all research | 36 | 37.5% | 26.39% | 0% | 0% | 0% | 0% | 63.89%
1.9 | Prepare Master Plan & Detail Plan | 5 | 0% | 0% | 0% | 0% | 40% | 40% | 80%
1.10 | Prepare and Update Configuration Management | 5 | 0% | 0% | 20% | 40% | 40% | 0% | 100%
1.11 | Prepare and Update Communication Management | 5 | 0% | 0% | 20% | 0% | 20% | 20% | 60%
1.12 | Prepare and Update Change Management | 5 | 0% | 0% | 20% | 40% | 0% | 40% | 100%
1.13 | Prepare and Update Risk Management | 5 | 0% | 0% | 20% | 40% | 0% | 40% | 100%
1.14 | Prepare and Update Project Plan | 5 | 0% | 0% | 20% | 0% | 0% | 80% | 100%
1.15 | Identify Process & Quality Management | 2 | 0% | 0% | 0% | 0% | 0% | 50% | 50%
1.16 | Gather High Level Requirement | 3 | 0% | 0% | 66.67% | 0% | 0% | 0% | 66.67%
1.17 | Draw Business Process and Verifiy with Customer | 2 | 0% | 0% | 0% | 0% | 50% | 0% | 50%
Insert new rows above this one
|  | Cumulative EV | 13.5 | 9.5 | 7 | 6 | 6 | 12
Actual Cost for Week 3
Actual Cost (AC) of Work Performed
WBS | Task Name |  | 2018-10-22 | 2018-10-23 | 2018-10-24 | 2018-10-25 | 2018-10-26 | 2018-10-27 | Status
1.8 | Team Training Phase 3 - Review all research | 23 | 13.5 | 9.5 |  |  |  |  | Close
1.9 | Prepare Master Plan & Detail Plan | 4 |  |  |  |  | 2 | 2 | Close
1.10 | Prepare and Update Configuration Management | 5 |  |  | 1 | 2 | 2 |  | Close
1.11 | Prepare and Update Communication Management | 3 |  |  | 1 |  | 1 | 1 | Close
1.12 | Prepare and Update Change Management | 5 |  |  | 1 | 2 |  | 2 | Close
1.13 | Prepare and Update Risk Management | 5 |  |  | 1 | 2 |  | 2 | Close
1.14 | Prepare and Update Project Plan | 5 |  |  | 1 |  |  | 4 | Close
1.15 | Identify Process & Quality Management | 1 | [5 empty] | 1 | Close
1.16 | Gather High Level Requirement | 2 |  |  | 2 |  |  |  | Close
1.17 | Draw Business Process and Verifiy with Customer | 1 |  |  |  |  | 1 |  | Close
Insert new rows above this one
|  | Total Actual Cost | 13.5 | 9.5 | 7 | 6 | 6 | 12
|  | Cumulative Actual Cost (AC) | 13.5 | 23 | 30 | 36 | 42 | 54

## W4
Earned Value for Week 4
Cumulative Earned Value (EV)
WBS | Task Name | Total Hour | 2018-10-29 | 2018-10-30 | 2018-10-31 | 2018-11-01 | 2018-11-02 | 2018-11-03 | Total
1.17 | Draw Business Process and Verifiy with Customer | 4 | 25% | 25% | 25% | 0% | 0% | 0% | 75%
1.18 | Update Document for Project | 5 | 0% | 0% | 40% | 20% | 20% | 20% | 100%
1.19 | Team Training Phase 4 - Research & Demo Login Function | 72 | 0% | 0% | 0% | 30.56% | 31.94% | 27.78% | 90.28%
1.20 | Update Business Process | 2 | 0% | 0% | 0% | 50% | 0% | 50% | 100%
1.21 | Identify Architecture Phase 1 - Identify Constraint and Quality | 2 | 0% | 0% | 0% | 0% | 0% | 50% | 50%
1.22 | Do Process and Quality Management | 1 | 0% | 0% | 0% | 0% | 0% | 100% | 100%
Insert new rows above this one
|  | Cumulative EV | 1 | 1 | 3 | 24 | 24 | 24
Actual Cost for Week 4
Actual Cost (AC) of Work Performed
WBS | Task Name |  | 2018-10-29 | 2018-10-30 | 2018-10-31 | 2018-11-01 | 2018-11-02 | 2018-11-03 | Status
1.17 | Draw Business Process and Verifiy with Customer | 3 | 1 | 1 | 1 |  |  |  | Close
1.18 | Update Document for Project | 5 |  |  | 2 | 1 | 1 | 1 | Close
1.19 | Team Training Phase 4 - Research & Demo Login Function | 65 |  |  |  | 22 | 23 | 20 | Close
1.20 | Update Business Process | 2 |  |  |  | 1 |  | 1 | Close
1.21 | Identify Architecture Phase 1 - Identify Constraint and Quality | 1 | [5 empty] | 1 | Close
1.22 | Do Process and Quality Management | 1 | [5 empty] | 1 | Close
Insert new rows above this one
|  | Total Actual Cost | 1 | 1 | 3 | 24 | 24 | 24
|  | Cumulative Actual Cost (AC) | 1 | 2 | 5 | 29 | 53 | 77

## W5
Earned Value for Week 5
Cumulative Earned Value (EV)
WBS | Task Name | Total Hour | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-10 | Total
1.19 | Team Training Phase 4 - Research & Demo Login Function | 72 | 33.33% | 33.33% | 20.83% | 0% | 0% | 0% | 87.5%
1.20 | Update Business Process | 4 | 0% | 0% | 75% | 0% | 0% | 0% | 75%
1.21 | Identify Architecture Phase 1 - Identify Constraint and Quality | 4 | 0% | 0% | 75% | 0% | 0% | 0% | 75%
1.22 | Do Process and Quality Management | 4 | 0% | 0% | 75% | 0% | 0% | 0% | 75%
1.23 | Identify Architecture Phase 2 - Continues to identify Quality | 5 | 0% | 0% | 0% | 40% | 40% | 20% | 100%
1.24 | Prepare Architecture Design Template | 3 | 0% | 0% | 0% | 0% | 33.33% | 66.67% | 100%
1.25 | Write and Prove Scenario for Security Attribute for Customer | 4 | 0% | 0% | 0% | 25% | 25% | 25% | 75%
1.26 | Research about N - Tier Architecture | 8 | 0% | 0% | 0% | 0% | 50% | 50% | 100%
1.27 | Research about RealTime Pattern | 8 | 0% | 0% | 0% | 0% | 37.5% | 37.5% | 75%
1.28 | Research about Unit of Works Layer | 4 | 0% | 0% | 0% | 0% | 50% | 25% | 75%
1.29 | Research about Repository Layer | 4 | 0% | 0% | 0% | 0% | 50% | 50% | 100%
1.30 | Research about Business Layer | 4 | 0% | 0% | 0% | 0% | 50% | 50% | 100%
1.31 | Update Architect Driver Document | 1 | 0% | 0% | 0% | 0% | 0% | 100% | 100%
1.32 | Research ReactNative | 6 | 0% | 0% | 0% | 0% | 50% | 50% | 100%
1.33 | Support Research ReactNative | 6 | 0% | 0% | 0% | 0% | 50% | 50% | 100%
0%
Insert new rows above this one
|  | Cumulative EV | 24 | 24 | 24 | 3 | 23 | 23
Actual Cost for Week 5
Actual Cost (AC) of Work Performed
WBS | Task Name |  | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-10 | Status
1.19 | Team Training Phase 4 - Research & Demo Login Function | 63 | 24 | 24 | 15 |  |  |  | Close
1.20 | Update Business Process | 3 |  |  | 3 |  |  |  | Close
1.21 | Identify Architecture Phase 1 - Identify Constraint and Quality | 3 |  |  | 3 |  |  |  | Close
1.22 | Do Process and Quality Management | 3 |  |  | 3 |  |  |  | Close
1.23 | Identify Architecture Phase 2 - Continues to identify Quality | 5 |  |  |  | 2 | 2 | 1 | On-Going
1.24 | Prepare Architecture Design Template | 3 |  |  |  |  | 1 | 2 | On-Going
1.25 | Write and Prove Scenario for Security Attribute for Customer | 3 |  |  |  | 1 | 1 | 1 | On-Going
1.26 | Research about N - Tier Architecture | 8 |  |  |  |  | 4 | 4 | On-Going
1.27 | Research about RealTime Pattern | 6 |  |  |  |  | 3 | 3 | On-Going
1.28 | Research about Unit of Works Layer | 3 |  |  |  |  | 2 | 1 | On-Going
1.29 | Research about Repository Layer | 4 |  |  |  |  | 2 | 2 | On-Going
1.30 | Research about Business Layer | 4 |  |  |  |  | 2 | 2 | On-Going
1.31 | Update Architect Driver Document | 1 | [5 empty] | 1 | On-Going
1.32 | Research ReactNative | 6 |  |  |  |  | 3 | 3 | On-Going
1.33 | Support Research ReactNative | 6 |  |  |  |  | 3 | 3 | On-Going
Insert new rows above this one
|  | Total Actual Cost | 24 | 24 | 24 | 3 | 23 | 23
|  | Cumulative Actual Cost (AC) | 24 | 48 | 72 | 75 | 98 | 121

## W6
Earned Value for Week 6
Cumulative Earned Value (EV)
WBS | Task Name | Total Hour | 2018-11-12 | 2018-11-13 | 2018-11-14 | 2018-11-15 | 2018-11-16 | 2018-11-17 | Total
1.23 | Identify Architecture Phase 2 - Continues to identify Quality | 5 | 40% | 20% | 20% | 20% | 0% | 0% | 100%
1.24 | Prepare Architecture Design Template | 2 | 0% | 50% | 0% | 0% | 50% | 0% | 100%
1.25 | Write and Prove Scenario for Security Attribute for Customer | 1 | 100% | 0% | 0% | 0% | 0% | 0% | 100%
1.26 | Research about N - Tier Architecture | 24 | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 12.5% | 95.83%
1.27 | Research about RealTime Pattern | 24 | 12.5% | 16.67% | 16.67% | 16.67% | 16.67% | 12.5% | 91.67%
1.28 | Research about Unit of Works Layer | 14 | 14.29% | 0% | 21.43% | 21.43% | 21.43% | 21.43% | 100%
1.29 | Research about Repository Layer | 14 | 7.143% | 14.29% | 14.29% | 21.43% | 21.43% | 14.29% | 92.86%
1.30 | Research about Business Layer | 14 | 14.29% | 14.29% | 14.29% | 21.43% | 21.43% | 7.143% | 92.86%
1.31 | Update Architect Driver Document | 3 | 100% | 0% | 0% | 0% | 0% | 0% | 100%
1.32 | Research ReactNative | 18 | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 100%
1.33 | Support Research ReactNative | 18 | 16.67% | 16.67% | 16.67% | 16.67% | 11.11% | 16.67% | 94.44%
0%
Insert new rows above this one
|  | Cumulative EV | 24 | 20 | 22 | 24 | 23 | 18
Actual Cost for Week 6
Actual Cost (AC) of Work Performed
WBS | Task Name |  | 2018-11-12 | 2018-11-13 | 2018-11-14 | 2018-11-15 | 2018-11-16 | 2018-11-17 | Status
1.23 | Identify Architecture Phase 2 - Continues to identify Quality | 5 | 2 | 1 | 1 | 1 |  |  | Close
1.24 | Prepare Architecture Design Template | 2 |  | 1 |  |  | 1 |  | Close
1.25 | Write and Prove Scenario for Security Attribute for Customer | 1 | 1 | [5 empty] | Close
1.26 | Research about N - Tier Architecture | 23 | 4 | 4 | 4 | 4 | 4 | 3 | Close
1.27 | Research about RealTime Pattern | 22 | 3 | 4 | 4 | 4 | 4 | 3 | Close
1.28 | Research about Unit of Works Layer | 14 | 2 |  | 3 | 3 | 3 | 3 | Close
1.29 | Research about Repository Layer | 13 | 1 | 2 | 2 | 3 | 3 | 2 | Close
1.30 | Research about Business Layer | 13 | 2 | 2 | 2 | 3 | 3 | 1 | Close
1.31 | Update Architect Driver Document | 3 | 3 | [5 empty] | Close
1.32 | Research ReactNative | 18 | 3 | 3 | 3 | 3 | 3 | 3 | Close
1.33 | Support Research ReactNative | 17 | 3 | 3 | 3 | 3 | 2 | 3 | Close
Insert new rows above this one
|  | Total Actual Cost | 24 | 20 | 22 | 24 | 23 | 18
|  | Cumulative Actual Cost (AC) | 24 | 44 | 66 | 90 | 113 | 131

## W7
Earned Value for Week 7
Cumulative Earned Value (EV)
WBS | Task Name | Total Hour | 2018-11-19 | 2018-11-20 | 2018-11-21 | 2018-11-22 | 2018-11-23 | 2018-11-24 | Total
1.34 | Identify about more Quality of System and Pattern | 108 | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 15.74% | 99.07%
1.35 | Identify and Write Scenario for Quality Compatibility, Performance, Maintainability,Authenticity | 12 | 0% | 0% | 16.67% | 25% | 25% | 25% | 91.67%
1.36 | Research about Micro Service Pattern | 4 | 0% | 0% | 25% | 25% | 25% | 25% | 100%
Insert new rows above this one
|  | Cumulative EV | 18 | 18 | 21 | 22 | 22 | 21
Actual Cost for Week 7
Actual Cost (AC) of Work Performed
WBS | Task Name |  | 2018-11-19 | 2018-11-20 | 2018-11-21 | 2018-11-22 | 2018-11-23 | 2018-11-24 | Status
1.34 | Identify about more Quality of System and Pattern | 107 | 18 | 18 | 18 | 18 | 18 | 17 | Close
1.35 | Identify and Write Scenario for Quality Compatibility, Performance, Maintainability,Authenticity | 11 |  |  | 2 | 3 | 3 | 3 | Close
1.36 | Research about Micro Service Pattern | 4 |  |  | 1 | 1 | 1 | 1 | Close
Insert new rows above this one
|  | Total Actual Cost | 18 | 18 | 21 | 22 | 22 | 21
|  | Cumulative Actual Cost (AC) | 18 | 36 | 57 | 79 | 101 | 122

## W8
Earned Value for Week 8
Cumulative Earned Value (EV)
WBS | Task Name | Total Hour | 2018-11-26 | 2018-11-27 | 2018-11-28 | 2018-11-29 | 2018-11-30 | 2018-12-01 | Total
1.36 | Research about Micro Service Pattern | 2 | 100% | 0% | 0% | 0% | 0% | 0% | 100%
1.37 | Identify Architecture Phase 3 - Make Design View to solve the Constraint, Quality and High Level Requirement | 20 | 0% | 25% | 25% | 25% | 25% | 0% | 100%
1.38 | Gather Requirement for Core System | 3 | 0% | 33.33% | 66.67% | 0% | 0% | 0% | 100%
1.39 | Confirm Identified Qualities for System | 2 | 0% | 0% | 0% | 100% | 0% | 0% | 100%
1.40 | Draw Business Process for API Core System ( User, Role, Domain ) | 20 | 0% | 0% | 0% | 30% | 30% | 30% | 90%
1.41 | Review Static View of System | 2 | 0% | 0% | 0% | 0% | 0% | 100% | 100%
Insert new rows above this one
|  | Cumulative EV | 2 | 6 | 7 | 13 | 11 | 8
Actual Cost for Week 8
Actual Cost (AC) of Work Performed
WBS | Task Name |  | 2018-11-26 | 2018-11-27 | 2018-11-28 | 2018-11-29 | 2018-11-30 | 2018-12-01 | Status
1.36 | Research about Micro Service Pattern | 2 | 2 | [5 empty] | Close
1.37 | Identify Architecture Phase 3 - Make Design View to solve the Constraint, Quality and High Level Requirement | 20 |  | 5 | 5 | 5 | 5 |  | Close
1.38 | Gather Requirement for Core System | 3 |  | 1 | 2 |  |  |  | Close
1.39 | Confirm Identified Qualities for System | 2 |  |  |  | 2 |  |  | Close
1.40 | Draw Business Process for API Core System ( User, Role, Domain ) | 18 |  |  |  | 6 | 6 | 6 | Close
1.41 | Review Static View of System | 2 | [5 empty] | 2 | Close
Insert new rows above this one
|  | Total Actual Cost | 2 | 6 | 7 | 13 | 11 | 8
|  | Cumulative Actual Cost (AC) | 2 | 8 | 15 | 28 | 39 | 47

## W9
Earned Value for Week 9
Cumulative Earned Value (EV)
WBS | Task Name | Total Hour | 2018-12-03 | 2018-12-04 | 2018-12-05 | 2018-12-06 | 2018-12-07 | 2018-12-08 | Total
1.42 | Draw Business Process for API Core System ( Login, Register) | 70 | 17.14% | 0% | 17.14% | 0% | 0% | 0% | 34.29%
1.43 | Implement Microservice for Login, Register using Token | 70 | 17.14% | 17.14% | 17.14% | 0% | 0% | 0% | 51.43%
1.44 | Confirm Architecture View for System | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Insert new rows above this one
|  | Cumulative EV | 24 | 12 | 24 | 0 | 0 | 0
Actual Cost for Week 9
Actual Cost (AC) of Work Performed
WBS | Task Name |  | 2018-12-03 | 2018-12-04 | 2018-12-05 | 2018-12-06 | 2018-12-07 | 2018-12-08 | Status
1.42 | Draw Business Process for API Core System ( Login, Register) | 24 | 12 |  | 12 |  |  |  | On-Going
1.43 | Implement Microservice for Login, Register using Token | 36 | 12 | 12 | 12 |  |  |  | On-Going
1.44 | Confirm Architecture View for System | 0 | [6 empty] | On-Going
Insert new rows above this one
|  | Total Actual Cost | 24 | 12 | 24 | 0 | 0 | 0
|  | Cumulative Actual Cost (AC) | 24 | 36 | 60 | 60 | 60 | 60