## Total
Residential Communication Channel
Earned Value Analysis Report
| Prepared By: | Vinh Nguyen
| Date: | 2018-06-11
[42]
| For Period: | Iteration 2
Note:
Tuần 10 - 15 : Sẽ có 6 ngày làm việc ( trừ CN) và quy định mỗi thành viên làm việc 4h/ ngày, tổng số thành viên làm việc 24h/ ngày và 1 tuần sẽ là 144h/ tuần.
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | Total Hour | W10 | W11 | W12 | W13 | W14 | W15
2.1 | Confirm Requirement for Core API | 2 | 2
2.2 | Design Activity flow for Core API phase 1
2.2.1 | Design flow for User | 16 | 16
2.2.2 | Design flow for Role | 20 | 20
2.2.3 | Design flow for Domain | 20 | 20
2.2.4 | Design flow for Login | 20 | 20
2.3 | Requirement Specification for Core API phase 1
2.3.1 | Design UseCase for Core API | 20 | 20
2.3.2 | Revise Specification Document | 10 | 10
2.3.3 | Update System Context | 4 | 4
2.4 | Review Activity Flow of Core API | 3 | 3
2.5 | Review Requirement Specification for Core API | 3 | 3
2.6 | Create Feature Tree for Core API | 5 | 5
2.7 | Refine Specification Document | 5 | 5
2.8 | Create List API Method | 12 |  |  |  | 12
2.9 | Create List API Function | 12 |  |  |  | 2
2.10 | Create Authentication
2.10.1 | Create Token Authentication | 24 |  |  |  | 24
2.10.2 | Create Owin Identity | 24 |  |  |  | 24
2.11 | Create Properties Role, User, Domain | 8 |  |  |  | 8
2.12 | Update Core Activity Flow | 24 |  |  |  | 24
2.13 | Update Quality Management Document | 12 |  |  |  | 12
2.14 | Update Architecture Design and Driver | 12 |  |  |  | 12
2.15 | Implement Core API | 240 |  |  |  |  | 240
2.15.1 | Develop User API | 48 |  |  |  |  | 48
2.15.2 | Develop Role API | 48 |  |  |  |  | 48
2.15.3 | Develop Domain API | 48 |  |  |  |  | 48
2.15.4 | Develop UserRole API | 48 |  |  |  |  | 48
2.15.5 | Develop Login API | 48 |  |  |  |  | 48
2.16 | Prepare Test Plan | 24 |  |  |  |  | 24
Insert new rows above this one
| Total Hour | 760 | 128 | 0 | 0 | 118 | 504 | 0
|  | Cumulative Planned Value (PV) | 128 | 128 | 128 | 246 | 750 | 750
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 125 | 125 | 125 | 251 | 251 | 251
|  | Cumulative Earned Value (EV) | 125 | 0 | 0 | 126 | 0 | 0
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | 0 | -125 | -125 | -125 | -251 | -251
|  | Schedule Variance (SV = EV - PV) | -3 | -128 | -128 | -120 | -750 | -750
|  | Cost Performance Index (CPI = EV/AC) | 1 | 0 | 0 | 0.50199 | 0 | 0
|  | Schedule Performance Index (SPI = EV/PV) | 0.97656 | 0 | 0 | 0.5122 | 0 | 0
|  | Estimated Cost at Completion (EAC) | 760 | #DIV/0! | #DIV/0! | 1513.9683 | #DIV/0! | #DIV/0!
Note on A21: Work Breakdown Structure (WBS)

## AC
Actual Cost for Iteration 2
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period.
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Transfer the Cumulative Actual Cost to the Report worksheet.
Actual Cost (AC) of Work Performed
WBS | Task Name | Total | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15
2.1 | Confirm Requirement for Core API | 2 | 2
2.2 | Design Activity flow for Core API phase 1
2.2.1 | Design flow for User | 16 | 16
2.2.2 | Design flow for Role | 20 | 20
2.2.3 | Design flow for Domain | 20 | 20
2.2.4 | Design flow for Login | 20 | 20
2.3 | Requirement Specification for Core API phase 1
2.3.1 | Design UseCase for Core API | 20 | 20
2.3.2 | Revise Specification Document | 8 | 8
2.3.3 | Update System Context | 3 | 3
2.4 | Review Activity Flow of Core API | 3 | 3
2.5 | Review Requirement Specification for Core API | 3 | 3
2.6 | Create Feature Tree for Core API | 5 | 5
2.7 | Refine Specification Document | 5 | 5
2.8 | Create List API Method | 12 |  |  |  | 12
2.9 | Create List API Function | 12 |  |  |  | 12
2.10 | Create Authentication | 0 |  |  |  | 0
2.10.1 | Create Token Authentication | 24 |  |  |  | 24
2.10.2 | Create Owin Identity | 24 |  |  |  | 24
2.11 | Create Properties Role, User, Domain | 8 |  |  |  | 8
2.12 | Update Core Activity Flow | 24 |  |  |  | 24
2.13 | Update Quality Management Document | 12 |  |  |  | 12
2.14 | Update Architecture Design and Driver | 10 |  |  |  | 10
2.15 | Implement Core API | 0
2.15.1 | Develop User API | 0
2.15.2 | Develop Role API | 0
2.15.3 | Develop Domain API | 0
2.15.4 | Develop UserRole API | 0
2.15.5 | Develop Login API | 0
2.16 | Prepare Test Plan | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
Insert new rows above this one
|  | Total Actual Cost | 125 | 0 | 0 | 126 | 0 | 0
|  | Cumulative Actual Cost (AC) | 125 | 125 | 125 | 251 | 251 | 251

## EV
Earned Value for Iteration 1
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP).
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV)
WBS | Task Name | Total Hour | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15
2.1 | Confirm Requirement for Core API | 2 | 100%
2.2 | Design Activity flow for Core API phase 1 | 0 | 0%
2.2.1 | Design flow for User | 16 | 100%
2.2.2 | Design flow for Role | 20 | 100%
2.2.3 | Design flow for Domain | 20 | 100%
2.2.4 | Design flow for Login | 20 | 100%
2.3 | Requirement Specification for Core API phase 1 | 0 | 0%
2.3.1 | Design UseCase for Core API | 20 | 100%
2.3.2 | Revise Specification Document | 10 | 80%
2.3.3 | Update System Context | 4 | 75%
1.11 | Review Activity Flow of Core API | 3 | 100%
2.5 | Review Requirement Specification for Core API | 3 | 100%
2.6 | Create Feature Tree for Core API | 5 | 100%
2.7 | Refine Specification Document | 5 | 100%
2.8 | Create List API Method | 12 |  |  |  | 100%
2.9 | Create List API Function | 12 |  |  |  | 100%
2.10 | Create Authentication | 0 |  |  |  | 0%
2.10.1 | Create Token Authentication | 24 |  |  |  | 100%
2.10.2 | Create Owin Identity | 24 |  |  |  | 100%
2.11 | Create Properties Role, User, Domain | 8 |  |  |  | 100%
2.12 | Update Core Activity Flow | 24 |  |  |  | 100%
2.13 | Update Quality Management Document | 12 |  |  |  | 100%
2.14 | Update Architecture Design and Driver | 12 |  |  |  | 83.33%
2.15 | Implement Core API | 240
2.15.1 | Develop User API | 48
2.15.2 | Develop Role API | 48
2.15.3 | Develop Domain API | 48
2.15.4 | Develop UserRole API | 48
2.15.5 | Develop Login API | 48
2.16 | Prepare Test Plan | 24
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
Insert new rows above this one
|  | Cumulative EV | 125 | 0 | 0 | 126 | 0 | 0
Open
On-Going
Close
Re-Open

## W10
Earned Value for Week 10
Cumulative Earned Value (EV)
WBS | Task Name | Total Hour | 2018-12-10 | 2018-12-11 | 2018-12-12 | 2018-12-13 | 2018-12-14 | 2018-12-15 | Total
2.1 | Confirm Requirement for Core API | 2 | 100% | 0% | 0% | 0% | 0% | 0% | 100%
2.2 | Design Activity flow for Core API phase 1
2.2.1 | Design flow for User | 16 | 25% | 25% | 0% | 25% | 25% | 0% | 100%
2.2.2 | Design flow for Role | 20 | 20% | 20% | 20% | 20% | 20% | 0% | 100%
2.2.3 | Design flow for Domain | 20 | 20% | 0% | 20% | 20% | 20% | 20% | 100%
2.2.4 | Design flow for Login | 20 | 0% | 20% | 20% | 20% | 20% | 20% | 100%
2.3 | Requirement Specification for Core API phase 1
2.3.1 | Design UseCase for Core API | 20 | 0% | 20% | 20% | 20% | 20% | 20% | 100%
2.3.2 | Revise Specification Document | 10 | 0% | 40% | 40% | 0% | 0% | 0% | 80%
2.3.3 | Update System Context | 4 | 0% | 0% | 0% | 0% | 0% | 75% | 75%
2.4 | Review Activity Flow of Core API | 3 | 0% | 0% | 0% | 0% | 33.33% | 66.67% | 100%
2.5 | Review Requirement Specification for Core API | 3 | 0% | 0% | 0% | 0% | 33.33% | 66.67% | 100%
2.6 | Create Feature Tree for Core API | 5 | 60% | 0% | 0% | 0% | 0% | 40% | 100%
2.7 | Refine Specification Document | 5 | 40% | 0% | 0% | 0% | 0% | 60% | 100%
Insert new rows above this one
|  | Cumulative EV | 19 | 20 | 20 | 20 | 22 | 24
Actual Cost for Week 10
Actual Cost (AC) of Work Performed
WBS | Task Name |  | 2018-12-10 | 2018-12-11 | 2018-12-12 | 2018-12-13 | 2018-12-14 | 2018-12-15 | Status
2.1 | Confirm Requirement for Core API | 2 | 2 | [5 empty] | Close
2.2 | Design Activity flow for Core API phase 1 | [7 empty] | Close
2.2.1 | Design flow for User | 16 | 4 | 4 |  | 4 | 4 |  | Close
2.2.2 | Design flow for Role | 20 | 4 | 4 | 4 | 4 | 4 |  | Close
2.2.3 | Design flow for Domain | 20 | 4 |  | 4 | 4 | 4 | 4 | Close
2.2.4 | Design flow for Login | 20 |  | 4 | 4 | 4 | 4 | 4 | Close
2.3 | Requirement Specification for Core API phase 1 | [7 empty] | Close
2.3.1 | Design UseCase for Core API | 20 |  | 4 | 4 | 4 | 4 | 4 | Close
2.3.2 | Revise Specification Document | 8 |  | 4 | 4 |  |  |  | Close
2.3.3 | Update System Context | 3 | [5 empty] | 3 | Close
2.4 | Review Activity Flow of Core API | 3 |  |  |  |  | 1 | 2 | Close
2.5 | Review Requirement Specification for Core API | 3 |  |  |  |  | 1 | 2 | Close
2.6 | Create Feature Tree for Core API | 5 | 3 |  |  |  |  | 2 | Close
2.7 | Refine Specification Document | 5 | 2 |  |  |  |  | 3 | Close
Insert new rows above this one
|  | Total Actual Cost | 19 | 20 | 20 | 20 | 22 | 24
|  | Cumulative Actual Cost (AC) | 19 | 39 | 59 | 79 | 101 | 125

## W11
Earned Value for Week 11
Cumulative Earned Value (EV)
WBS | Task Name | Total Hour | 2018-12-17 | 2018-12-18 | 2018-12-19 | 2018-12-20 | 2018-12-21 | 2018-12-22 | Total
|  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Insert new rows above this one
|  | Cumulative EV | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Actual Cost for Week 11
Actual Cost (AC) of Work Performed
WBS | Task Name |  | 2018-12-17 | 2018-12-18 | 2018-12-19 | 2018-12-20 | 2018-12-21 | 2018-12-22 | Status
|  | 0 | [6 empty] | Close
Insert new rows above this one
|  | Total Actual Cost | 0 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Actual Cost (AC) | 0 | 0 | 0 | 0 | 0 | 0

## W12
Earned Value for Week 12
Cumulative Earned Value (EV)
WBS | Task Name | Total Hour | 2018-12-24 | 2018-12-25 | 2018-12-26 | 2018-12-27 | 2018-12-28 | 2018-12-29 | Total
|  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Insert new rows above this one
|  | Cumulative EV | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Actual Cost for Week 12
Actual Cost (AC) of Work Performed
WBS | Task Name |  | 2018-12-24 | 2018-12-25 | 2018-12-26 | 2018-12-27 | 2018-12-28 | 2018-12-29 | Status
|  | 0 | [6 empty] | Close
|  | 0 | [6 empty] | Close
|  | 0 | [6 empty] | Close
|  | 0 | [6 empty] | Close
|  | 0 | [6 empty] | Close
|  | 0 | [6 empty] | Close
|  | 0 | [6 empty] | Close
|  | 0 | [6 empty] | Close
|  | 0 | [6 empty] | Close
|  | 0 | [6 empty] | Close
Insert new rows above this one
|  | Total Actual Cost | 0 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Actual Cost (AC) | 0 | 0 | 0 | 0 | 0 | 0

## W13
Earned Value for Week 13
Cumulative Earned Value (EV)
WBS | Task Name | Total Hour | 2018-12-31 | 2019-01-01 | 2019-01-02 | 2019-01-03 | 2019-01-04 | 2019-01-05 | Total
2.8 | Create List API Method | 12 | 0% | 0% | 0% | 50% | 50% | 0% | 100%
2.9 | Create List API Function | 12 | 0% | 0% | 0% | 50% | 50% | 0% | 100%
2.10 | Create Authentication
2.10.1 | Create Token Authentication | 24 | 25% | 0% | 25% | 25% | 0% | 25% | 100%
2.10.2 | Create Owin Identity | 24 | 25% | 0% | 25% | 25% | 25% | 0% | 100%
2.11 | Create Properties Role, User, Domain | 8 | 0% | 0% | 0% | 0% | 0% | 100% | 100%
2.12 | Update Core Activity Flow | 24 | 25% | 0% | 25% | 0% | 25% | 25% | 100%
2.13 | Update Quality Management Document | 12 | 50% | 0% | 50% | 0% | 0% | 0% | 100%
2.14 | Update Architecture Design and Driver | 12 | 0% | 50% | 0% | 0% | 0% | 33.33% | 83.33%
Insert new rows above this one
|  | Cumulative EV | 24 | 6 | 24 | 24 | 24 | 24
Actual Cost for Week 13
Actual Cost (AC) of Work Performed
WBS | Task Name |  | 2018-12-31 | 2019-01-01 | 2019-01-02 | 2019-01-03 | 2019-01-04 | 2019-01-05 | Status
2.8 | Create List API Method | 12 |  |  |  | 6 | 6 |  | Close
2.9 | Create List API Function | 12 |  | 0 |  | 6 | 6 |  | Close
2.10 | Create Authentication | [7 empty] | Close
2.10.1 | Create Token Authentication | 24 | 6 |  | 6 | 6 |  | 6 | Close
2.10.2 | Create Owin Identity | 24 | 6 |  | 6 | 6 | 6 |  | Close
2.11 | Create Properties Role, User, Domain | 8 | [5 empty] | 8 | Close
2.12 | Update Core Activity Flow | 24 | 6 |  | 6 |  | 6 | 6 | Close
2.13 | Update Quality Management Document | 12 | 6 |  | 6 |  |  |  | Close
2.14 | Update Architecture Design and Driver | 10 |  | 6 |  |  |  | 4 | Close
Insert new rows above this one | [8 empty] | Close
|  | Total Actual Cost | 24 | 6 | 24 | 24 | 24 | 24
|  | Cumulative Actual Cost (AC) | 24 | 30 | 54 | 78 | 102 | 126

## W14
Earned Value for Week 14
Cumulative Earned Value (EV)
WBS | Task Name | Total Hour | 2019-01-07 | 2019-01-08 | 2019-01-09 | 2019-01-10 | 2019-01-11 | 2019-01-12 | Total
2.15 | Implement Core API
2.15.1 | Develop User API | 48 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.15.2 | Develop Role API | 48 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.15.3 | Develop Domain API | 48 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.15.4 | Develop UserRole API | 48 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.15.5 | Develop Login API | 48 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.16 | Prepare Test Plan | 24 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Insert new rows above this one
|  | Cumulative EV | 0 | 0 | 0 | 0 | 0 | 0
Actual Cost for Week 14
Actual Cost (AC) of Work Performed
WBS | Task Name |  | 2019-01-07 | 2019-01-08 | 2019-01-09 | 2019-01-10 | 2019-01-11 | 2019-01-12 | Status
2.15 | Implement Core API | [7 empty] | Close
2.15.1 | Develop User API | 0 | [6 empty] | Close
2.15.2 | Develop Role API | 0 | [6 empty] | Close
2.15.3 | Develop Domain API | 0 | [6 empty] | Close
2.15.4 | Develop UserRole API | 0 | [6 empty] | On-Going
2.15.5 | Develop Login API | 0 | [6 empty] | On-Going
2.16 | Prepare Test Plan | 0 | [6 empty] | On-Going
Insert new rows above this one
|  | Total Actual Cost | 0 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Actual Cost (AC) | 0 | 0 | 0 | 0 | 0 | 0

## W15
Earned Value for Week 15
Cumulative Earned Value (EV)
WBS | Task Name | Total Hour | 2019-01-14 | 2019-01-15 | 2019-01-16 | 2019-01-17 | 2019-01-18 | 2019-01-19 | Total
2.14 | Update Architecture Design and Driver | 5 | 40% | 20% | 20% | 20% | 0% | 0% | 100%
2.15 | Implement Core API | 2 | 0% | 50% | 0% | 0% | 50% | 0% | 100%
2.15.1 | Develop User API | 1 | 100% | 0% | 0% | 0% | 0% | 0% | 100%
2.15.2 | Develop Role API | 24 | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 12.5% | 95.83%
2.15.3 | Develop Domain API | 24 | 12.5% | 16.67% | 16.67% | 16.67% | 16.67% | 12.5% | 91.67%
2.15.4 | Develop UserRole API | 14 | 14.29% | 0% | 21.43% | 21.43% | 21.43% | 21.43% | 100%
2.15.5 | Develop Login API | 14 | 7.143% | 14.29% | 14.29% | 21.43% | 21.43% | 14.29% | 92.86%
2.16 | Prepare Test Plan | 14 | 14.29% | 14.29% | 14.29% | 21.43% | 21.43% | 7.143% | 92.86%
- | - | 3 | 100% | 0% | 0% | 0% | 0% | 0% | 100%
- | - | 18 | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 100%
- | - | 18 | 16.67% | 16.67% | 16.67% | 16.67% | 11.11% | 16.67% | 94.44%
0%
Insert new rows above this one
|  | Cumulative EV | 24 | 20 | 22 | 24 | 23 | 18
Actual Cost for Week 15
Actual Cost (AC) of Work Performed
WBS | Task Name |  | 2019-01-14 | 2019-01-15 | 2019-01-16 | 2019-01-17 | 2019-01-18 | 2019-01-19 | Status
1.23 | Update Architecture Design and Driver | 5 | 2 | 1 | 1 | 1 |  |  | Close
2.15 | Implement Core API | 2 |  | 1 |  |  | 1 |  | Close
2.15.1 | Develop User API | 1 | 1 | [5 empty] | Close
2.15.2 | Develop Role API | 23 | 4 | 4 | 4 | 4 | 4 | 3 | Close
2.15.3 | Develop Domain API | 22 | 3 | 4 | 4 | 4 | 4 | 3 | Close
2.15.4 | Develop UserRole API | 14 | 2 |  | 3 | 3 | 3 | 3 | Close
2.15.5 | Develop Login API | 13 | 1 | 2 | 2 | 3 | 3 | 2 | Close
2.16 | Prepare Test Plan | 13 | 2 | 2 | 2 | 3 | 3 | 1 | Close
- | - | 3 | 3 | [5 empty] | Close
- | - | 18 | 3 | 3 | 3 | 3 | 3 | 3 | Close
- | - | 17 | 3 | 3 | 3 | 3 | 2 | 3 | Close
Insert new rows above this one
|  | Total Actual Cost | 24 | 20 | 22 | 24 | 23 | 18
|  | Cumulative Actual Cost (AC) | 24 | 44 | 66 | 90 | 113 | 131