## Overal
PROJECT MASTER PLAN
Project Name |  |  | Residential Communication Channel |  | Overall Weeks
Project Manager Name |  |  | Vinh Nguyen |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30
Iterarion | Status | Tasks |  | Assigned to
1 | On-going | Prepare document, training for project Architecture Design Functional Requirement in High Level |  | GENTLEMAN TEAM | Overall Weeks Week 1: Wed 10/10/18; Overall Weeks Week 2: X; Overall Weeks Week 3: Wed 24/10/18; Overall Weeks Week 4: Thu 1/11/18; Overall Weeks Week 5: Thu 8/11/18; Overall Weeks Week 6: Thu 15/11/18; Overall Weeks Week 7: Thu 22/11/18; Overall Weeks Week 8: Thu 29/11/18; Overall Weeks Week 9: Thu 6/12/18
2 | Open | Development Libraries for Core System |  | GENTLEMAN TEAM | Overall Weeks Week 10: Thu 13/12/18; Overall Weeks Week 11: X; Overall Weeks Week 12: Sat 29/12/18; Overall Weeks Week 13: Thu 3/1/19
3 | Open | Development Feature Chat, Notification & User Dashboard |  | GENTLEMAN TEAM | bar: Overall Weeks Week 16 to Overall Weeks Week 21
4 | Open | Development Feature left |  | GENTLEMAN TEAM | bar: Overall Weeks Week 22 to Overall Weeks Week 30
Open
On-going
Close

## Calendar
WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3
2018-10-07 | 2018-10-08 | 2018-10-09 | 2018-10-10 | 2018-10-11 | 2018-10-12 | 2018-10-13 | 2018-10-14 | 2018-10-15 | 2018-10-16 | 2018-10-17 | 2018-10-18 | 2018-10-19 | 2018-10-20 | 2018-10-21 | 2018-10-22 | 2018-10-23 | 2018-10-24 | 2018-10-25 | 2018-10-26 | 2018-10-27
WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6
2018-10-28 | 2018-10-29 | 2018-10-30 | 2018-10-31 | 2018-11-01 | 2018-11-02 | 2018-11-03 | 2018-11-04 | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-10 | 2018-11-11 | 2018-11-12 | 2018-11-13 | 2018-11-14 | 2018-11-15 | 2018-11-16 | 2018-11-17
WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9
2018-11-18 | 2018-11-19 | 2018-11-20 | 2018-11-21 | 2018-11-22 | 2018-11-23 | 2018-11-24 | 2018-11-25 | 2018-11-26 | 2018-11-27 | 2018-11-28 | 2018-11-29 | 2018-11-30 | 2018-12-01 | 2018-12-02 | 2018-12-03 | 2018-12-04 | 2018-12-05 | 2018-12-06 | 2018-12-07 | 2018-12-08
WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12
2018-12-09 | 2018-12-10 | 2018-12-11 | 2018-12-12 | 2018-12-13 | 2018-12-14 | 2018-12-15 | 2018-12-16 | 2018-12-17 | 2018-12-18 | 2018-12-19 | 2018-12-20 | 2018-12-21 | 2018-12-22 | 2018-12-23 | 2018-12-24 | 2018-12-25 | 2018-12-26 | 2018-12-27 | 2018-12-28 | 2018-12-29
WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15
2018-12-30 | 2018-12-31 | 2019-01-01 | 2019-01-02 | 2019-01-03 | 2019-01-04 | 2019-01-05 | 2019-01-06 | 2019-01-07 | 2019-01-08 | 2019-01-09 | 2019-01-10 | 2019-01-11 | 2019-01-12 | 2019-01-13 | 2019-01-14 | 2019-01-15 | 2019-01-16 | 2019-01-17 | 2019-01-18 | 2019-01-19
WEEK 16 | [6 empty] | WEEK 17 | [6 empty] | WEEK 18
2018-01-20 | 2018-01-21 | 2018-01-22 | 2018-01-23 | 2018-01-24 | 2018-01-25 | 2018-01-26 | 2019-02-17 | 2019-02-18 | 2019-02-19 | 2019-02-20 | 2019-02-21 | 2019-02-22 | 2019-02-23 | 2019-02-24 | 2019-02-25 | 2019-02-26 | 2019-02-27 | 2019-02-28 | 2019-03-01 | 2019-03-02
WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21
2019-03-03 | 2019-03-04 | 2019-03-05 | 2019-03-06 | 2019-03-07 | 2019-03-08 | 2019-03-09 | 2019-03-10 | 2019-03-11 | 2019-03-12 | 2019-03-13 | 2019-03-14 | 2019-03-15 | 2019-03-16 | 2019-03-17 | 2019-03-18 | 2019-03-19 | 2019-03-20 | 2019-03-21 | 2019-03-22 | 2019-03-23
WEEK 22 | [6 empty] | WEEK 23 | [6 empty] | WEEK 24
2019-03-24 | 2019-03-25 | 2019-03-26 | 2019-03-27 | 2019-03-28 | 2019-03-29 | 2019-03-30 | 2019-03-31 | 2019-04-01 | 2019-04-02 | 2019-04-03 | 2019-04-04 | 2019-04-05 | 2019-04-06 | 2019-04-07 | 2019-04-08 | 2019-04-09 | 2019-04-10 | 2019-04-11 | 2019-04-12 | 2019-04-13
WEEK 25 | [6 empty] | WEEK 26 | [6 empty] | WEEK 27
2019-04-14 | 2019-04-15 | 2019-04-16 | 2019-04-17 | 2019-04-18 | 2019-04-19 | 2019-04-20 | 2019-04-21 | 2019-04-22 | 2019-04-23 | 2019-04-24 | 2019-04-25 | 2019-04-26 | 2019-04-27 | 2019-04-28 | 2019-04-29 | 2019-04-30 | 2019-05-01 | 2019-05-02 | 2019-05-03 | 2019-05-04
WEEK 28 | [6 empty] | WEEK 29 | [6 empty] | WEEK 30
2019-05-05 | 2019-05-06 | 2019-05-07 | 2019-05-08 | 2019-05-09 | 2019-05-10 | 2019-05-11 | 2019-05-12 | 2019-05-13 | 2019-05-14 | 2019-05-15 | 2019-05-16 | 2019-05-17 | 2019-05-18 | 2019-05-19 | 2019-05-20 | 2019-05-21 | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-25