## Excel Milestone Tracker
RESIDENTIAL COMMUNICATION CHANNEL
PROJECT TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE
2018-10-08 | Kick Off | 5 | 1
2018-10-08 | Iteration 1: Preparation | -5 | 1
2018-10-24 | Iteration 1: High - Level Requirement | 15 | 1
2018-10-27 | End of Preparation Phase | -10 | 1
2018-11-01 | Iteration 1: Architecture and Quality Management | 5 | 1
2018-11-25 | Iteration 2: Analyze Requirement for Core System | 10 | 1
2018-12-09 | End of Iteration 1 | -5 | 1
2018-12-09 | Iteration 2: Develop Libraries of Core System | 20 | 1
2019-01-20 | End of Iteration 2 | -10 | 1
2019-01-20 | Iteration 3: Analyze Requirement and Develop Feature Chat, Notification & Dashboard for User | 15 | 1
2019-01-28 | Lunar New Year | 5 | 1
2019-02-17 | End of Lunar New Year | -5 | 1
2019-02-17 | Iteration 3: Continue Developing Features | 25 | 1
2019-03-24 | End of Iteration 3 | -5 | 1
2019-03-24 | Iteration 4: Develop Special Feature for the System | 15 | 1
2019-05-05 | End of Iteration 4 | -15 | 1
2019-05-05 | Buffer Time for Project | 10 | 1
2019-05-25 | Release Product and Sign Off | 20 | 1
3 Easy steps to instantly turn Excel data into a PowerPoint slide
1. Download the Free Office Timeline plug-in for PowerPoint - 14-day Trial Edition..
2. Open PowerPoint and click on NEW Timeline from the Office Timeline tab inside of PowerPoint.
Copy your Excel Milestone Tracker table and paste it into Office Timeline with the PASTE button.
3. Click the green SAVE button to instantly produce you timeline slide.