## Week 4
MEETING MINUTE
Team 1: Communication Channel
Date: | 30/10/2018 |  |  | Location: | Phòng 2.7
Attendees: | Mr.Quoc, GENTLEMAN TEAM
Summary:
1/
2/
3/
Last week tasks: | [5 empty] | This week tasks:
| 1/ Chuẩn bị các tài liệu cần thiết cho dự án | [5 empty] | 1/ Cập nhật các tài liệu theo yêu cầu
|  | Target date: | 27/10/18 |  |  |  |  | Target date: | 2018-05-11
|  | Status: | DONE |  |  |  |  | Status: | ON-GOING
|  | Description: | [5 empty] | Description:
| 2/ Chuẩn bị Master Plan và Detail Plan | [5 empty] | 2/ Thay đổi Detail Plan
|  | Target date: | 27/10/18 |  |  |  |  | Target date: | 2018-05-11
|  | Status: | DONE |  |  |  |  | Status: | ON-GOING
|  | Description: | [5 empty] | Description:
| 3/ Xác định các Iteration | [5 empty] | 3/ Define Process và Quality Management cho dự án
|  | Target date: | 27/10/18 |  |  |  |  | Target date: | 2018-05-11
|  | Status: | DONE |  |  |  |  | Status: | ON-GOING
|  | Description: | [5 empty] | Description:
4/ Define Process và Quality Management cho dự án
|  | Target date: | 27/10/2018
|  | Status: | ON-GOING
Description:

## Week5
MEETING MINUTE
Team 1: Communication Channel
Date: | 2018-11-06 |  |  | Location: | Phòng 2.7
Attendees: | Mr.Quoc, GENTLEMAN TEAM
Summary:
1/
2/
3/
Last week tasks: | [5 empty] | This week tasks:
| 1/ Cập nhật các tài liệu theo yêu cầu | [5 empty] | 1/ Baseline Configuration Management
|  | Target date: | 2018-05-11 |  |  |  |  | Target date: | dd/mm/yy
|  | Status: | DONE |  |  |  |  | Status: | OPEN
|  | Description: | [5 empty] | Description:
| 2/ Thay đổi Detail Plan | [5 empty] | 2/ Basline High Level Requirement
|  | Target date: | 2018-05-11 |  |  |  |  | Target date: | 13/11/18
|  | Status: | DONE |  |  |  |  | Status: | ON-GOING
|  | Description: | [5 empty] | Description:
3/ Làm implementation và xác định Risk
| 3/ Define Process và Quality Management cho dự án | [6 empty] | Target date: | 13/11/18
|  | Target date: | 2018-05-11 |  |  |  |  | Status: | ON-GOING
|  | Status: | ON-GOING |  |  |  |  | Description:
|  | Description: |  |  |  |  | 4/ Làm Process and Quality Management
[8 empty] | Target date: | 13/11/18
[8 empty] | Status: | DONE
Description:
5/ Tạo Group chat trên Mesenger ( Involve GENTLEMAN + Mentor + KH)
[8 empty] | Target date: | 13/11/18
[8 empty] | Status: | DONE
Description:
6/ Prepare Architecure Template, Quality Scenario
[8 empty] | Target date: | 13/11/18
[8 empty] | Status: | ON-GOING
Description:

## Week6
MEETING MINUTE
Team 1: Communication Channel
Date: | 2018-11-13 |  |  |  | Location: | Phòng 2.7
Attendees: | Mr.Quoc, GENTLEMAN TEAM
Summary:
1/
2/
3/
Last week tasks: | [6 empty] | This week tasks:
| 1/ Baseline Configuration Management | [6 empty] | 1/
|  | Target date: | 13/11/18 | [5 empty] | Target date: | dd/mm/yy
|  | Status: | ON-GOING | [5 empty] | Status: | OPEN
|  | Description: | [6 empty] | Description:
| 2/ Basline High Level Requirement | [6 empty] | 2/
|  | Target date: | 13/11/18 | [5 empty] | Target date:
|  | Status: | DONE | [5 empty] | Status: | ON-GOING
|  | Description: | [6 empty] | Description:
| 3/ Làm implementation và xác định Risk |  |  | ( Không hiểu cách làm Implementation ) |  |  |  | 3/
|  | Target date: | 13/11/18 | [5 empty] | Target date:
|  | Status: | DONE | [5 empty] | Status: | ON-GOING
|  | Description: | [6 empty] | Description:
| 4/ Làm Process and Quality Management |  |  | ( Bản Draft ) |  |  |  | 4/
|  | Target date: | 13/11/18 | [5 empty] | Target date:
|  | Status: | DONE | [5 empty] | Status: | DONE
|  | Description: | [6 empty] | Description:
| 5/ Tạo Group chat trên Mesenger ( Involve GENTLEMAN + Mentor + KH) | [6 empty] | 5/
|  | Target date: | 13/11/18 | [5 empty] | Target date:
|  | Status: | DONE | [5 empty] | Status: | DONE
|  | Description: | [6 empty] | Description:
| 6/ Prepare Architecure Template, Quality Scenario | [6 empty] | 6/
|  | Target date: | 13/11/18 | [5 empty] | Target date:
|  | Status: | DONE | [5 empty] | Status: | ON-GOING
|  | Description: | [6 empty] | Description:

## Week7
MEETING MINUTE
Team 1: Communication Channel
Date: | 2018-11-20 |  |  |  | Location: | Phòng 2.7
Attendees: | Mr.Quoc, GENTLEMAN TEAM
Summary:
1/
2/
3/
Last week tasks: | [6 empty] | This week tasks:
| 1/ Baseline Configuration Management | [6 empty] | 1/
|  | Target date: | 13/11/18 | [5 empty] | Target date: | dd/mm/yy
|  | Status: | ON-GOING | [5 empty] | Status: | OPEN
|  | Description: | [6 empty] | Description:
| 2/ Basline High Level Requirement | [6 empty] | 2/
|  | Target date: | 13/11/18 | [5 empty] | Target date:
|  | Status: | DONE | [5 empty] | Status: | ON-GOING
|  | Description: | [6 empty] | Description:
| 3/ Làm implementation và xác định Risk |  |  | ( Không hiểu cách làm Implementation ) |  |  |  | 3/
|  | Target date: | 13/11/18 | [5 empty] | Target date:
|  | Status: | DONE | [5 empty] | Status: | ON-GOING
|  | Description: | [6 empty] | Description:
| 4/ Làm Process and Quality Management |  |  | ( Bản Draft ) |  |  |  | 4/
|  | Target date: | 13/11/18 | [5 empty] | Target date:
|  | Status: | DONE | [5 empty] | Status: | DONE
|  | Description: | [6 empty] | Description:
| 5/ Tạo Group chat trên Mesenger ( Involve GENTLEMAN + Mentor + KH) | [6 empty] | 5/
|  | Target date: | 13/11/18 | [5 empty] | Target date:
|  | Status: | DONE | [5 empty] | Status: | DONE
|  | Description: | [6 empty] | Description:
| 6/ Prepare Architecure Template, Quality Scenario | [6 empty] | 6/
|  | Target date: | 13/11/18 | [5 empty] | Target date:
|  | Status: | DONE | [5 empty] | Status: | ON-GOING
|  | Description: | [6 empty] | Description: